Monthly Expenditure Report  Municipality Kareeberg

Municipality & Code  :   NC074

Month: November 2011

| Part 1: | Financial Information |
| --- | --- |

| A | B | C | D | E | F |
| --- | --- | --- | --- | --- | --- |
| 2011/12 Allocation | Received / Transferred to Date | Expenditure this month | Total expenditure for previous months | Overall expenditure to date | Available Balance |
| 1,200,000 | 1,200,000 | 437,306.43 | 258,244.13 | 695,550.56 | 504,449.44 |

| Part 2: | Reasons for variance |
| --- | --- |

|  | Reasons for variance |
| --- | --- |
| 1 |  |
| 2 |  |
| 3 |  |

| Part 3: | Progress Information |
| --- | --- |

| List of Projects | Amount Budgeted | Progress Details | Remedial Measures if no Progress |
| --- | --- | --- | --- |
| LED | R400,000 | R99,423.10 |  |
| Ward Committees | R200,000 | R100,000.00 |  |
| Capacity Building | R270,000 | Nil |  |
| Installation Prepaid Electricity meters | R270,000 | R174,656.49 |  |
| Regular water samples | R 60,000 | R14,635.48 |  |
| PMS |  | R48,591.36 |  |

Part 4: Signature

_________________________			P.B. Rossouw							30-11-2011

CFO Signature				 	Name & Surname 						Date (dd / mm / yyyy)