## Project details
MUNICIPAL INFRASTRUCTURE GRANT MONTHLY AND QUARTERLY REPORTING TEMPLATE
|  |  | MUNICIPALITY: | Kareeberg NC074 |  | MONTH: | June 2014
MIS Form ID | Nat / Prov Project Registration Number (as on the registration letter) | Project location: Ward No and Village Name (MIG1 - 3.3) | Project Title | MIG Category (B,P or E) | Project Type (water, sanitation etc) | New / Rehabilitate | Bulk Project (Yes / No) | Internal Reticulation (Yes / No) | Rural / Urban | EPWP (Yes / No) | Planned poor households benefitted or km's roads constructed | Planned poor households benefitted or km's roads constructed in 2013/14 FY | Progress in previous FY(s) - Poor households benefitted or km's roads constructed | Progress in current FY - Poor households benefitted or km's roads constructed | Project Status (Not registered, Registered, Design & Tender, Contractor appointed, Construction <=25%, <=50%, <=75%, <=99%, completed, retention) | Project start date yy-mm-dd | Project end date yy-mm-dd | Total Project Cost | Registered MIG Funds | Counter Funding | Budgeted MIG Funds (2014/15) | Total Actual Expenditure on MIG funds in Previous FYs (incl 2013/14) | Current FY - Total Actual Expenditure on MIG funds in the 2014/15 FY | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | Reason for variance (per project) | Remedial action (per project) | PREVIOUS EMPLOYMENT FIGURES (person days) | [6 empty] | EMPLOYMENT FIGURES (person days) | [6 empty] | Balans 1 Julie 2014 | Balans uitstaande
[38 empty] | Adult Men | Adult Women | Young Men | Young Women | PWD Men | PWD Women | Total | Adult Men | Adult Women | Young Men | Young Women | PWD Men | PWD Women | Total
MIG 1 |  |  | MIG 1 or PMU | MIG 1 - 3.2 | MIG 1 - 3.4 | MIG 1 - 3.2 | MIG 1 - 6. | MIG 1 - 6. | MIG 1 - 3.2 | MIG 1 - 3.2 | MIG 1 - 4.1 |  |  |  |  | As per IP | As per IP | MIG1 - 3.4 | MIG 1 - 3.4 | MIG 1 - 3.4 | As per IP
147671 | CS/NC/2354/07/09 | Carnarvon Ward 2 | Upgrading of Sport Complex | B | Sport & Recreation | New |  | No | Rural | No |  |  |  |  | Construction | June 2007 |  | 4547597 | 4547597 | - |  | 3782503.29 | 0 | 2013-07-01: 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765093.71 | 765093.71
1068 | MIG/NC0359/R,ST/10/13 | Carnarvon Ward 2 | Streets and Stormwater | B | Roads | New |  | No | Rural | No |  |  |  |  | Construction | Dec 2011 |  | 11083630.63 | 10870313 | - |  | 11083630.63 | 0 | 2013-07-01: 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -213317.63 | -213317.63
1082 | MIG/NC0357/R,ST/11/13 | Vanwyksvlei Ward 4 | Streets and Stormwater | B | Roads | New |  | No | Rural | No |  |  |  |  | Construction | Apr 2012 |  | 6729239 | 6729239 | - |  | 2309229.46 | 0 | 2013-07-01: 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4420009.54 | 4420009.54
195946 | MIG/NC0358/R,ST/11/13 | Vosburg Ward 3 | Streets and Stormwater | B | Roads | New |  | No | Rural | No |  |  |  |  | Construction | Apr 2012 |  | 6211606 | 6211606 | - |  | 4137613.57 | 0 | 2013-07-01: 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2073992.43 | 2073992.43
[23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHIEF FINANCIAL OFFICER
NAME: |  | PB Rossouw
SIGNATURE:
DATE: |  | 31-07-2014
CONTACT DETAILS: |  | 053 382 3012
SIGNED BY MUNICIPAL MANAGER (Or delegated person, include letter of delegation)
NAME: |  | A van Schalkwyk
SIGNATURE:
DATE: |  | 31-07-2014
CONTACT DETAILS: |  | 053 382 3012
Note on K5: LesegoM: Is the project registered on the EPWP Database?

## Completed
MUNICIPAL INFRASTRUCTURE GRANT MONTHLY AND QUARTERLY REPORTING TEMPLATE
|  |  | MUNICIPALITY: | Kareeberg |  | MONTH: | July 2014
MIS Form ID | Nat / Prov Project Registration Number (as on the registration letter) | Project location: Ward No and Village Name (MIG1 - 3.3) | Project Title | MIG Category (B,P or E) | Project Type (water, sanitation etc) | New / Rehabilitate | Bulk Project (Yes / No) | Internal Reticulation (Yes / No) | Rural / Urban | EPWP (Yes / No) | Planned poor households or km's | Progress in previous FY(s) - Poor households benefitted or km's roads constructed | Progress in current FY - Poor households benefitted or km's roads constructed | Project Status | Project start date yy-mm-dd | Project end date yy-mm-dd | Total Project Cost | Registered MIG Funds | Counter Funding | Total Actual Expenditure on MIG funds in Previous FYs (incl 2012/13) | PREVIOUS EMPLOYMENT FIGURES (person days)
[21 empty] | Adult Men | Adult Women | Young Men | Young Women | PWD Men | PWD Women | Total
MIG 1 |  |  | MIG 1 or PMU | MIG 1 - 3.2 | MIG 1 - 3.4 | MIG 1 - 3.2 | MIG 1 - 6. | MIG 1 - 6. | MIG 1 - 3.2 | MIG 1 - 3.2 | MIG 1 - 4.1 |  |  |  | As per IP | As per IP | MIG1 - 3.4 | MIG 1 - 3.4 | MIG 1 - 3.4
C/NC0166/W/02/04
MIG/NC0156/S/07/10
MIGNC0172/S/07/09
MIG/NC0182/S/07/08
MIG/NC0299/S/09/10
MIG/NC0297/SW/09/11
MIG/NC0298/SW/09/10
MIG/NC0338/CL//10/12
MIG/NC0366/CL/10/12
MIG/NC0337/CL/10/11
MIG/NC0391/S/10/12
MIG/NC0466/CL/12/13
CHIEF FINANCIAL OFFICER
NAME:
SIGNATURE:
DATE:
CONTACT DETAILS:
SIGNED BY MUNICIPAL MANAGER (Or delegated person, include letter of delegation)
NAME:
SIGNATURE:
DATE:
CONTACT DETAILS:
Note on B5: : As appearing on the project approval letter.
Note on K5: LesegoM: Is the project registered on the EPWP Database?