## Project details
MUNICIPAL INFRASTRUCTURE GRANT MONTHLY AND QUARTERLY REPORTING TEMPLATE
|  |  | MUNICIPALITY: | Kareeberg NC074 |  | MONTH: | November 2014
MIS Form ID | Nat / Prov Project Registration Number (as on the registration letter) | Project location: Ward No and Village Name (MIG1 - 3.3) | Project Title | MIG Category (B,P or E) | Project Type (water, sanitation etc) | New / Rehabilitate | Bulk Project (Yes / No) | Internal Reticulation (Yes / No) | Rural / Urban | EPWP (Yes / No) | Planned poor households benefitted or km's roads constructed | Planned poor households benefitted or km's roads constructed in 2013/14 FY | Progress in previous FY(s) - Poor households benefitted or km's roads constructed | Progress in current FY - Poor households benefitted or km's roads constructed | Project Status (Not registered, Registered, Design & Tender, Contractor appointed, Construction <=25%, <=50%, <=75%, <=99%, completed, retention) | Project start date yy-mm-dd | Project end date yy-mm-dd | Total Project Cost | Registered MIG Funds | Counter Funding | Budgeted MIG Funds (2014/15) | Total Actual Expenditure on MIG funds in Previous FYs (incl 2013/14) | Current FY - Total Actual Expenditure on MIG funds in the 2014/15 FY | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01 | 2013-11-01 | 2013-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | Reason for variance (per project) | Remedial action (per project) | PREVIOUS EMPLOYMENT FIGURES (person days) | [6 empty] | EMPLOYMENT FIGURES (person days) | [6 empty] | Balans 1 Julie 2014 | Balans uitstaande 30-11-2014
[38 empty] | Adult Men | Adult Women | Young Men | Young Women | PWD Men | PWD Women | Total | Adult Men | Adult Women | Young Men | Young Women | PWD Men | PWD Women | Total
MIG 1 |  |  | MIG 1 or PMU | MIG 1 - 3.2 | MIG 1 - 3.4 | MIG 1 - 3.2 | MIG 1 - 6. | MIG 1 - 6. | MIG 1 - 3.2 | MIG 1 - 3.2 | MIG 1 - 4.1 |  |  |  |  | As per IP | As per IP | MIG1 - 3.4 | MIG 1 - 3.4 | MIG 1 - 3.4 | As per IP
147671 | CS/NC/2354/07/09 | Carnarvon Ward 2 | Upgrading of Sport Complex | B | Sport & Recreation | New |  | No | Rural | No |  |  |  |  | Registered | June 2007 |  | 4547597 | 4547597 | - |  | 3782503.29 | 1548636.09 | 2013-07-01: 0; 2013-08-01: 956136; 2013-09-01: 537701.21; 2013-11-01: 54798.88 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765093.71 | -783542.38 | einde Augustus
218781 | MIG/NC0542/R,ST/14/16 | Carnarvon Ward 2 | Streets and Stormwater Phase 2 | B | Roads | New |  | No | Rural | No |  |  |  |  | Construction | 2014-07-01 |  | 12521288.75 | 10983586.62 | 1537702.13 |  | 0 | 2526786.7 | 2013-07-01: 0; 2013-08-01: 1451334.14; 2013-09-01: 517634.96; 2013-10-01: 349564.04; 2013-11-01: 208253.56 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10983586.62 | 8456799.92 | einde Junie
228121 | MIG/NC0541/R,ST/14/16 | Vanwyksvlei Ward 4 | Streets and Stormwater Phase 2 | B | Roads | New |  | No | Rural | No |  |  |  |  | Registered | 2014-07-01 |  | 8158068.92 | 8158068.92 | 0 |  | 0 | 0 | 2013-07-01: 0; 2013-08-01: 0; 2013-09-01: 0
1082 | MIG/NC0357/R,ST/11/13 | Vanwyksvlei Ward 4 | Streets and Stormwater | B | Roads | New |  | No | Rural | No |  |  |  |  | Construction | Apr 2012 |  | 6729239 | 6729239 | - |  | 2309229.46 | 0 | 2013-07-01: 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4420009.54 | 4420009.54
195946 | MIG/NC0358/R,ST/11/13 | Vosburg Ward 3 | Streets and Stormwater | B | Roads | New |  | No | Rural | No |  |  |  |  | Construction | Apr 2012 |  | 6211606 | 6211606 | - |  | 4137613.57 | 0 | 2013-07-01: 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2073992.43 | 2073992.43
[23 empty] | 4075422.79 | 0 | 2407470.14 | 1055336.17 | 349564.04 | 263052.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHIEF FINANCIAL OFFICER
NAME: |  | PB Rossouw
SIGNATURE:
DATE: |  | 30-11-2014
CONTACT DETAILS: |  | 053 382 3012
SIGNED BY MUNICIPAL MANAGER (Or delegated person, include letter of delegation)
NAME: |  | A van Schalkwyk
SIGNATURE:
DATE: |  | 30-11-2014
CONTACT DETAILS: |  | 053 382 3012
Note on K5: LesegoM: Is the project registered on the EPWP Database?
Note on A9: MIG 1278
Note on A10: MIG 1279

## Completed
MUNICIPAL INFRASTRUCTURE GRANT MONTHLY AND QUARTERLY REPORTING TEMPLATE
|  |  | MUNICIPALITY: | Kareeberg |  | MONTH: | August 2014
MIS Form ID | Nat / Prov Project Registration Number (as on the registration letter) | Project location: Ward No and Village Name (MIG1 - 3.3) | Project Title | MIG Category (B,P or E) | Project Type (water, sanitation etc) | New / Rehabilitate | Bulk Project (Yes / No) | Internal Reticulation (Yes / No) | Rural / Urban | EPWP (Yes / No) | Planned poor households or km's | Progress in previous FY(s) - Poor households benefitted or km's roads constructed | Progress in current FY - Poor households benefitted or km's roads constructed | Project Status | Project start date yy-mm-dd | Project end date yy-mm-dd | Total Project Cost | Registered MIG Funds | Counter Funding | Total Actual Expenditure on MIG funds in Previous FYs (incl 2012/13) | PREVIOUS EMPLOYMENT FIGURES (person days)
[21 empty] | Adult Men | Adult Women | Young Men | Young Women | PWD Men | PWD Women | Total
MIG 1 |  |  | MIG 1 or PMU | MIG 1 - 3.2 | MIG 1 - 3.4 | MIG 1 - 3.2 | MIG 1 - 6. | MIG 1 - 6. | MIG 1 - 3.2 | MIG 1 - 3.2 | MIG 1 - 4.1 |  |  |  | As per IP | As per IP | MIG1 - 3.4 | MIG 1 - 3.4 | MIG 1 - 3.4
| C/NC0166/W/02/04 |  | 301: Carnarvon Bulk Water | B | Water |  |  |  | Rural | No |  |  |  | Completed |  |  | 8326500 | 7160790 | 1165710 | 5355657.13
| MIG/NC0156/S/07/10 |  | 272: Carnarvon/Bonteheuwel Sewer Reticulation 620 erven & outfall line, pump station, rising main | B | Sanitation |  |  |  | Rural | No |  |  |  | Completed |  |  | 19652230 | 19652230 | 0 | 19521542
| MIGNC0172/S/07/09 |  | 422: Carnarvon Rehab of Oxidation Pond system | B | Sanitation |  |  |  | Rural | No |  |  |  | Completed |  |  | 13541983.96 | 13541983.96 | 0 | 13541984
| MIG/NC0182/S/07/08 |  | 417: Carnarvon Eradication of 125 bucket toilets | B | Sanitation |  |  |  | Rural | No |  |  |  | Completed |  |  | 6847293.72 | 6847293.72 | 0 | 6847294
| MIG/NC0299/S/09/10 |  | 953: Vanwyksvlei Septic tank, sludge drying beds & lined evaporation pond | B | Sanitation |  |  |  | Rural | No |  |  |  | Completed |  |  | 640794 | 562100 | 78694 | 107692.83
| MIG/NC0297/SW/09/11 |  | 952: Vanwyksvlei solid waste site | B | Solid Waste Removal |  |  |  | Rural | No |  |  |  | Completed |  |  | 826500 | 826500 | 0 | 534797.62
| MIG/NC0298/SW/09/10 |  | 931: Vosburg solid waste site | B | Solid Waste Removal |  |  |  | Rural | No |  |  |  | Completed |  |  | 826500 | 725000 | 101500 | 599186.53
| MIG/NC0338/CL//10/12 |  | 1036: Carnarvon High Mast lights | B | Street/Community Lighting |  |  |  | Rural | No |  |  |  | Completed |  |  | 2033378 | 2033378 | 0 | 1747149.61
| MIG/NC0366/CL/10/12 |  | 1037: Vanwyksvlei High Mast lights | B | Street/Community Lighting |  |  |  | Rural | No |  |  |  | Completed |  |  | 1164712 | 1164712 | 0 | 953674.11
| MIG/NC0337/CL/10/11 |  | 1038: Vosburg High Mast Lights | B | Street/Community Lighting |  |  |  | Rural | No |  |  |  | Completed |  |  | 287793 | 287793 | 0 | 190734.82
| MIG/NC0391/S/10/12 |  | 11033: Vosburg Permitation & Upgrading of WWTW | B | Sanitation |  |  |  | Rural | No |  |  |  | Completed |  |  | 3874860 | 3399000 | 475860 | 2542774.3
| MIG/NC0466/CL/12/13 |  | MIG 1238: Carnarvon High Mast Lights | B | Street/Community Lighting |  |  |  | Rural | No |  |  |  | Completed |  |  | 1200135 | 1200135 | 0 | 1200134
1068 | MIG/NC0359/R,ST/10/13
CHIEF FINANCIAL OFFICER
NAME: |  | P.B. Rossouw
SIGNATURE:
DATE: |  | 29-08-2014
CONTACT DETAILS: |  | 053 382 3012
SIGNED BY MUNICIPAL MANAGER (Or delegated person, include letter of delegation)
NAME: |  | A van Schalkwyk
SIGNATURE:
DATE: |  | 29-08-2014
CONTACT DETAILS: |  | 053 382 3012
Note on B5: : As appearing on the project approval letter.
Note on K5: LesegoM: Is the project registered on the EPWP Database?