## Bulk Reporting (new)
| 2017/18 Bulk Infrastructure Monthly Report |  |  |  |  | BULK INFRASTRUCTURE - |  | Annexure C
| Municipality: | KAREEBERG |  |  |  | Contact Person | A van Schalkwyk
| Municipality No: | NC074 |  |  |  | Tel Number | 053 382 3012
| Month: | January 2018 |  |  |  | Fax Number | 053 382 3142
Project name | Upgrade of network in Carnarvon-dorp |  |  |  |  | email address | kareeberg@xsinet.co.za
Project type | Substation |  | Line
| Size/Capacity (MVA) |  | Length (km)
Project category | New |  | New
| Upgrade |  | Upgrade | X
| Refurbishment |  | Refurbishment
Project Duration | Start date | 2018-01-28 | Target Finish date | 2018-02-28
|  | Month |  |  |  | Year To Date
| Approved Budget | Transferred Capital | Actual Capital Expenditure | % Variance |  | Transferred Capital | Actual Capital Expenditure | % Variance
| 1000000 | 0 | 8464.5 | -8464% |  | 1000000 | 131843.18 | 868157%
| Actual Capital Expenditure % (Month) |  | #DIV/0! |  |  | Actual Capital Expenditure % (YTD) |  | 13.18%
Main Project stages | Overall status | Milestones | Project Plan | Actual Status in % | Progress status in detail:
Planning, Design and Procurement | 66.67% | Pre Engineering | 2017-09-15 | 100% | Project was advertised and tenders closed on the 4th of December 2017. Busy with the evaluation of tenders
|  | Design | 2017-10-20 | 100%
|  | Procurement | 2017-11-30 | 0%
SUBSTATION Construction/Execution | #DIV/0! | Civil Works
Steel Work
Primary stage
Secondary Stage
LINE Construction/Execution | 0% | Trenching
|  | Poles | 2018-02-20 | 0%
|  | Stringing | 2018-02-20
OVERALL PROJECT STATUS | 50% | Commissioning
Close-up
Variance Explanation (Reporting Month) | Reasons for variance (where variance is not equal to zero) |  |  |  | Corrective action to be taken to bring the project back to schedule (action to be taken to address reasons for variance)
Capital (Financial)
Project Work (Technical)
NB: | Please attach supporting documentation, invoices and bill of materials purchased
Explanatory Notes:
Municipality: New Municipality Name
Municipality Number: New Municipality Number
Transferred Capital and Planned Connections: As per approved project details attached in letter for the month and year to date
Actual Capital Expenditure and Connections Completed: Actual for the month and year to date
%Variance: Enter the percentage variance for the month of reporting
Project: Enter Project Name
Enter the project approval status
Pre-Engineering: Pre-engineering percentage progress
Design: Project design stage in percentages
Procurement: The status of the project in the procurement process in percentages
: Please attach supporting documents : invoices and list of bill of materials purchased
Construction: The Project construction progress in percentages
Commisioning: Project commisioning progress in percentages
Close-up: Has the project being officially closed?
Variance Explanation: State reasons for variance and corrective action taken or to be taken to bring the project back to schedule
Close-up: Has the project being officially closed?
Variance Explanation: State reasons for variance and corrective action taken or to be taken to bring the project back to schedule
Please tick relevant cells
Note on D18: Sebastian Khoza: Planned completion date of each milestone; this will assist us to see if the project is on schedule or otherwise
Note on E18: Sebastian Khoza: Actual status of physical project progress; where a milestone is not applicable for the project, "NA" should be put on the relevent cell
Note on F18: Sebastian Khoza: Provide detailed status of the physical progress of the project
Note on B36: Sebastian Khoza: Where the variance is not equal to zero, reasons have to be provided, and if the variance is due to technical reasons, then a reason must also be given for that.

## Checklist
Annexure C
BULK INFRASTRUCTURE CHECKLIST
1.Pre Engineering check list | Complete | Not complete | Not Applicable | % status
Environmental Impact Assessment (EIA) | √
2.Design
Preliminary designs and drawings | √
Final designs and drawings | √
3.Procument
Procurement of service providers |  | √
Procurement of materials |  |  | √
Delivery of materials |  |  | √
4.CONSTRUCTION
4.1. Civil Works stage
Site preparation and surface levelling
Installation of earth mat
Construction of control room
Cable trenches and foundations
All foundation neatly finished
Has Cable trenching been completed
Cable trenches covers fitted
Is Structure foundation completed
Is transformer bay foundation completed
Yard stone completed
Is substation fence installed and earthed
Gates lockable
Is Fire protection and oil drainage completed
Is Fire extinguishers installed
Is warning signs and notices installed
4.2. Steelwork stage
Is all Steelwork structure complete
Is all Steel structures leveled and straight
Beams correctly installed
Steelwork correctly assembled
Is all steel structures galvanized
Is substation equipment grounded: Steel structure
4.3. Primary plant Stage
Is power transformers installation complete
Is auxiliary transformer installation complete
Is current transformers installation complete
Is circuit breakers installation complete
Is voltage transformers installation complete
Is airbreak switches installation complete
Is Isolators / Earthswitches installation complete
Is Busbars installation complete
Is Insulators installation complete
Is substation equipment grounded :Transformers
Is metal-clad switchgear installation complete
Is substation equipment grounded: Metal-clad Switchgear
Is installation of high voltage cables completed
4.4.Secondary plant stage
Is Panels installed
Is secondary wiring from primary plant to feeder panels installed
Is panel wiring and cable check completed
Is protection relays installed
Is metering meters installed
Is Battery charger installed
Telecontrol (SCADA) equipment installed
4.4. Poles
Is excavations for poles pit completed
Is planting of poles completed
Is numbering of poles completed
4.5. Stringers and Droppers stage
Is overheadlines installed on a registered servitude
Is Stringing of lines and droppers completed
Is sag and tension of line correct
Is tension of droppers correct
Is all electrical clearance correct
Is ground clearance according to specification
Bird diverters or protection installed
Aircraft warning installed
5. Commissioning stage
Have all lights, plugs inspected and tested certificate of compliance issued
Has power transformers been tested
Has Circuit breakers been tested
Voltage transformers been tested
Current transformers been tested
Has the High Voltage cable been tested
Auto reclosers been tested
Isolators/Earthswitches been tested
Metal-clad switchgear been tested
Has protection settings correctly applied to relays
Protection relays been tested
Has programmable meters been programmed accordingly
Metering equipment been tested and calibrated
Telecontol (SCADA) been tested
Battery charger been tested
Is phasing been completed
All feeders correctly labeled
Has substation drawings updated before make alive
Has handover certificates, commissioning documents for service been done
Has substation made alive been done
Comment:

## M&E part
2017/18 - BULK INFRASTRUCTURE REPORTING TEMPLATE - Monthly register of workers on projects
Month of report | January 2018
Project Name: | Upgrading of network Carnarvon-dorp | Note: Must be unique name (Don't use the same name for two projects)
Project Number: | C00010Q | Note: Must be unique number (Don't use the same number for two projects)
Project Type: | Households | Note:(Households,schools or bulk infrastructure)
Source of Funding | DoE | Note:(Department of Energy, Eskom, Municipality, Donor,etc)
Province: | Northern Cape | Note: (for Eskom, do not use regions) |  |  |  | NATIONAL TARGETS
Total Project Expenditure for month: | 8465 | Note: Invoice or contract amount, only enter value, no leading R |  |  |  | Total number of Jobs | 7, 920
Physical Outputs: |  | Note: (Km's line, no of Trfmr's, connections etc) |  |  |  | BEE/BWO/SMME expenditure | 50% of amount allocated
Contractor's Name: | [5 empty] | Temporary employment (80%) | 6, 336
CIPRO company registration number | [5 empty] | Permanent employment (20%) | 1, 584 |  | Minimum daily wage (see guidelines)
Type of contractor |  | Note: whether BEE, BWO or SMME |  |  |  | Youth (18 to 35yrs) Employment (50%) | 3, 960 |  | Categories of Municipality | Wages per hour | Wages per day
Contract Number: | [5 empty] | Women (36 yrs and above) Employment (30%) | 2, 376 |  | A | R 10.68 | R 85.44
Invoice Number: | [5 empty] | Employment of people with disability (2%) | 158 |  | B | R 9.42 | R 75.36
Project Start Date: | 2018-01-20 | yyyy-mm-dd |  |  |  | Men (36 yrs and above) Employment (18%) | 1, 426 |  | C | R 8.70 | R 69.60
Project End Date: | 2018-02-28 | yyyy-mm-dd
Certified by Project Manager: | Mr JH Adams | Note: Name of Project Manager
Date of certification: | 2018-01-03 | yyyy-mm-dd
Municipal Manager's Signature:………………………………………. |  |  |  |  | Official Municipal Stamp: |  |  |  | Date:…………………………… |  |  | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:…………………………… | Municipal Manager's Signature:………………………………………. | Official Municipal Stamp: | Date:……………………………
Employment and Training
First Name | Last Name (Surname) | ID Number | Gender (Male-M) (Female-F) | Has Disability (Yes-Y) (No-N) | Type of job | Number of days worked | Daily Wage | Total Wages for the Month | Total training days | Accredited or non-accredited | Name of training provided
|  |  | Total Male:0 Female:0 | Total Yes:0 No:0 | Excavators, General Worker, Learnership, Electrician, CLO etc | 0 |  | 0 | 0